## Monthly Billing
| Contract Amt | % Complete | Earned Value | Previously Billed | Invoice | Retainage | Net Invoice
CLIN 0001 | 977000 | 74.02% | 723216.496 | 261144 | 462072.496 | 0% | 462072.496
CLIN 0002 | 619000 | 7.007% | 43373.5593 | 12939 | 30434.5593 |  | 30434.5593
Total | 1596000 |  | 766590.0553 | 274083 | 492507.0553 | 0 | 492507.0553
Projected Monthly Billings
| CLIN 0001 |  |  |  | CLIN 0002 |  |  |  | TOTAL
Month | Monthly % | Cumulative % | Monthly $ | Cumulative $ | Monthly % | Cumulative % | Monthly $ | Cumulative $ | Monthly % | Cumulative % | Monthly $ | Cumulative $
2025-09-01 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0
2025-10-01 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0
2025-11-01 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0
2025-12-01 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0 | 0
2026-01-01 | 6% | 6% | 58620 | 58620 | 4% | 4% | 24760 | 24760 | 5.224% | 5.224% | 83380 | 83380
2026-02-01 | 8% | 14% | 78160 | 136780 | 5% | 9% | 30950 | 55710 | 6.836% | 12.06% | 109110 | 192490
2026-03-01 | 9% | 23% | 87930 | 224710 | 7% | 16% | 43330 | 99040 | 8.224% | 20.29% | 131260 | 323750
2026-04-01 | 9% | 32% | 87930 | 312640 | 8% | 24% | 49520 | 148560 | 8.612% | 28.9% | 137450 | 461200
2026-05-01 | 9% | 41% | 87930 | 400570 | 8% | 32% | 49520 | 198080 | 8.612% | 37.51% | 137450 | 598650
2026-06-01 | 9% | 50% | 87930 | 488500 | 8% | 40% | 49520 | 247600 | 8.612% | 46.12% | 137450 | 736100
2026-07-01 | 8% | 58% | 78160 | 566660 | 8% | 48% | 49520 | 297120 | 8% | 54.12% | 127680 | 863780
2026-08-01 | 7% | 65% | 68390 | 635050 | 8% | 56% | 49520 | 346640 | 7.388% | 61.51% | 117910 | 981690
2026-09-01 | 6% | 71% | 58620 | 693670 | 7% | 63% | 43330 | 389970 | 6.388% | 67.9% | 101950 | 1083640
2026-10-01 | 6% | 77% | 58620 | 752290 | 7% | 70% | 43330 | 433300 | 6.388% | 74.29% | 101950 | 1185590
2026-11-01 | 6% | 83% | 58620 | 810910 | 7% | 77% | 43330 | 476630 | 6.388% | 80.67% | 101950 | 1287540
2026-12-01 | 5% | 88% | 48850 | 859760 | 7% | 84% | 43330 | 519960 | 5.776% | 86.45% | 92180 | 1379720
2027-01-01 | 5% | 93% | 48850 | 908610 | 6% | 90% | 37140 | 557100 | 5.388% | 91.84% | 85990 | 1465710
2027-02-01 | 4% | 97% | 39080 | 947690 | 5% | 95% | 30950 | 588050 | 4.388% | 96.22% | 70030 | 1535740
2027-03-01 | 3% | 100% | 29310 | 977000 | 5% | 100% | 30950 | 619000 | 3.776% | 100% | 60260 | 1596000

## POC Calc
Contract Amt
CLIN | 1 | EMCS System Upgrade | 977000
CLIN | 2 | Installation of EMCS System | 619000
1596000
Contract Amt
Subcontract | 1 | AES | 695000
Subcontract | 2 | Gresham Smith | 110875
805875
Engineering Milestone Tracker (feeds CLIN 0001 %)
| Weight | % Complete | Weighted Earned
Submittals / Product Data | 10% | 100% | 10%
Niagara N4 Station / Supervisor Setup | 15% | 14.29% | 2.143%
Graphics / UI Pages | 20% | 0% | 0%
Controller Database / Point Mapping | 20% | 20.11% | 4.021%
Sequences / Programming Templates | 15% | 25% | 3.75%
As-Builts / O&M /Password Turnover | 10% | 5% | 0.5%
AX JACE Recovery / Turnover | 10% | 0% | 0%
20.41%
Procurement / Material Receipt Tracker (feeds CLIN 0001 %)
| Receipt % | Weight | Earned
DDC Hardware | 100% | 85% | 85%
Installation Material | 80% | 15% | 12%
97%
|  | Weight | Earned
| Engineering | 30% | 6.124%
| Material | 70% | 67.9%
| Billing % for CLIN 0001 |  | 74.02%
Install Quantity-Based Progress (feeds CLIN 0002 %)
| Scope | Trunk (20%) | Controller (20%) | Wiring (25%) | P2P (25%) | Owner (10%) | Weight | Earned
AHUs | 20 | 9 | 0 | 0 | 0 | 0 | 25% | 2.25%
OAUs | 3 | 0 | 0 | 0 | 0 | 0 | 6% | 0%
ERV | 3 | 0 | 0 | 0 | 0 | 0 | 5% | 0%
VAVs | 189 | 127 | 0 | 0 | 0 | 0 | 35% | 4.704%
JACEs | 7 | 0 | 0 | 0 | 0 | 0 | 6% | 0%
Plant (CHWS, CWS, HWS) | 3 | 0 | 0 | 0 | 0 | 0 | 10% | 0%
SF, EF, TF | 31 | 0 | 0 | 0 | 0 | 0 | 8% | 0%
UH | 15 | 1 | 0 | 0 | 0 | 0 | 4% | 0.05333%
Other (Air Comp, Misc) | 1 | 0 | 0 | 0 | 0 | 0 | 1% | 0%
[5 empty] | Billing % for CLIN 0002 |  |  | 7.007%
Subcontract Cost vs Bill Tracking (AES + Gresham Smith)
AES Subcontract Value | 695000
AES Invoiced to Date (input) | 278100
AES Paid to Date (input) | 139050
AES Remaining | 555950
Item | Value
GS Subcontract Value | 110875
GS Invoiced to Date (input) | 1579.86
GS Paid to Date (input)
GS Remaining | 110875

## BOM
MASTER BILL OF MATERIAL
Item # | Application | Tag | Part no | Estimated Quantity | Quantity Shipped | Unit Cost / MSRP | Extended Cost | % Received | Earned % | Description | Manufacturer
1 | JACE | JACE-# | JCI-FXSC9BASE0 | 7 | 7 | 3007.9 | 21055.3 | 100% | 3.745% | FX90 Suppervisor Controller, Micro SD Card, 2 RS485, 2 10/100MB Ethernet Ports | Johnson Controls
2 | Device | - | FX-SC9CL100-0 | 3 | 3 | 7728.19 | 23184.57 | 100% | 4.123% | Core 100 Field Device license, 5000 points for FX90 Supervisor controller | Johnson Controls
3 | Device | - | FX-SC9CL025-0 | 4 | 4 | 2616.16 | 10464.64 | 100% | 1.861% | Core 25 Field Device license,1200 points for FX90 Supervisor controller | Johnson Controls
4 | Device | - | FX-SC8DL25-0 | 4 | 4 | 1480 | 5920 | 100% | 1.053% | License enabling an additional 25 field, device,1250 points for one FX80, initial | Johnson Controls
5 | Maintenance License | SMA | FX-SC9D100M1-0 | 3 | 3 | 1712.5 | 5137.5 | 100% | 0.9137% | Initial 1 year software maintenance, 100-199 field devices, FX90 supervisor controller | Johnson Controls
6 | Maintenance License | SMA | FX-SC9D025M1-0 | 4 | 4 | 428.15 | 1712.6 | 100% | 0.3046% | Initial 1 year software maintenance,FX90 with 25-99 field devices | Johnson Controls
7 | Programmable Controller | C-1 | F4-CGE09090-0G | 29 | 29 | 1892.89 | 54893.81 | 100% | 9.763% | General Purpose, 18-Points, 7 UI, 2 BI, 4 CO, 2 AO, 3 BO, BACnet/IP, BACnet/Sc, Real Time, 24VAC | Johnson Controls
8 | Programable Controller | C-1 | F4-CGE04060-0G | 34 | 34 | 1185 | 40290 | 100% | 7.165% | General Purpose, 10-Point, 3 UI, 1 BI, 4 CO, 2 BO, Bacnet/IP, Bacnet/SC, RealTime, 24VAC | Johnson Controls
9 | Programable Controller | C-1 | F4-CVE03050-0PG | 189 | 189 | 945 | 178605 | 100% | 31.76% | VAV Controller, INT ACT, POS FBK, DPT, Bacnet/IP, N2, 3UI, 2CO, 3BO, Real time, 24VAC | Johnson Controls
10 | I/O Module | IO-1 | F4-XPM09090-0G | 23 | 23 | 1313.72 | 30215.56 | 100% | 5.374% | IO Module, 18-Points, 7 UI, 2 BI, 4 CO, 2 AO, 3 BO, BACnet/MSTP, 24VAC | Johnson Controls
11 | I/O Module | IO-1 | F4-XPM04060-0G | 3 | 3 | 801.1 | 2403.3 | 100% | 0.4274% | IO Module, 10-Points, 3 UI, 1 BI, 4 CO, 2 BO, BACnet/MSTP, 24VAC | Johnson Controls
12 | Immersion Temperature Sensor | TS-1, TS-2 | TE-631AP-1 | 12 | 12 | 202.84 | 2434.08 | 100% | 0.4329% | Immersion Temperature Sensor, 1K Ni RTD, Well Insertion 6.00" Probe, Plastic Enclosure | Johnson Controls
13 | Duct Temperature Sensor | DAT, MAT, RAT, OAT | TE-6311M-1 | 284 | 284 | 56.89 | 16156.76 | 100% | 2.873% | Duct Temperature Sensor, 1K Ni RTD, 8.00" Probe, Metal Enclosure | Johnson Controls
14 | Zone Temp Sensor | ZN-T | NSB8BTN240-0G | 150 | 150 | 326.4 | 48960 | 100% | 8.707% | NS Series Network Temperature Sensor, BACnet MS/TP, LCD Fixed Segment Display, White, JCI Logo | Johnson Controls
15 | Zone Temp/CO2 Sensor | ZN-T/CO2 | NSB8BTC240-0G | 39 | 39 | 812 | 31668 | 100% | 5.632% | NS Series Network Temperature/CO2 Sensor, BACnet MS/TP, LCD Fixed Segment Display, White, JCI Logo | Johnson Controls
16 | Duct Static Pressure | DSP | DP140005U11D | 23 | 23 | 415 | 9545 | 100% | 1.698% | Differential Pressure Transducer, Low Pressure, Unidirectional, 0 IN. TO 5 IN. W.C., 0 VDC TO 5 VDC | Johnson Controls
17 | Current Switch & Relay Accessories | CS/R-1 THRU CS/R-7 | CSD-CA1G1-1 | 74 | 74 | 185 | 13690 | 100% | 2.435% | Enclosed Split Core AC Sensor, 1.25–135 A, Adj. switch setpoint, LED indication 24 VAC/VDC Single-Pole, Single-Throw (SPST), N.O. Relay | Johnson Controls
|  |  | CR-02400-0 | 54 | 54 | 52 | 2808 | 100% | 0.4994%
18 | Damper Actuator | OAD, EAD | M9220-GGA-3 | 79 | 79 | 485 | 38315 | 100% | 6.814% | Proportional Electric Spring Return Actuators | Johnson Controls
19 | Room Temp Sensor | ZN-T | A/1K-NI-R2 | 42 | 42 | 48 | 2016 | 100% | 0.3585% | 1,000 Ohm Nickel RTD, Room (R2) | ACI
20 | Differential Pressure Sensor | DPT-1 THRU DPT-3 | A/WPR2-100-20-LCD | 9 | 9 | 1250 | 11250 | 100% | 2.001% | Liquid differential pressure transmitter with LCD, Nema4X, jumper selectable outputs with pressure ranges of 50, 100, 250 and 500PSI ranges, 5' (1.5M) FT6 cable | ACI
21 | Differential Pressure Sensor | FILT-DP | A/DLP-010-W-U-D-A-3 | 29 | 29 | 275 | 7975 | 100% | 1.418% | Differential Pressure, (0.5% Acc), 1, 2, 5, 10 inWC (Default), LCD, Unidirectional (Default), Bidirectional (Selectable) | ACI
22 | Field Mounted Relay | FR-# | RIBU1C | 48 | 48 | 43.15 | 2071.2 | 100% | 0.3683% | Pilot Relay, 10 Amp SPDT, 10-30 Vac/dc/ 120 Vac Coil, NEMA 1 Housing | Functional Devices
23 | Field Mounted Relay | FR-1 | RIB2401D | 26 | 26 | 58.5 | 1521 | 100% | 0.2705% | Pilot Relay, 10 Amp DPDT, 24 Vac/dc/ 120 Vac Coil | Functional Devices
[7 empty] | Goes to POC Calcualtion |  | 100%

## 3064
| CONTRACT PROGRESS SCHEDULE | [10 empty] | Form Approved
| (See Contractor's Instructions on Reverse) | [10 empty] | OMB NO. 0704-0188
Public reporting burden for this collection of information is estimated to average 15 minutes per response, including the time for reviewing instructions, searching existing data sources, gathering maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden to Department of Defense, Washington Headquarters Services, Directorate for information, Operations and Reports, 1215 Jefferson Davis Highway, Suite 1204, Arlington VA 22202-4302, and to the Office of Management and Budget, Paperwork Reduction Project 0704-0188, Washington DC 20503. Please DO NOT RETURN your form/questionnaire to either of these addresses. Send your completed form/questionnaire to: SAF/AQCP, 1060 Air Force Pentagon, Washington DC 20330-1060.
1. CONTRACT NO. |  |  | 8. PROJECT TITLE | [5 empty] | 10. APPROVAL RECOMMENDED BY:
FA28235C0048 |  |  | EMCS System Upgrade / Installation of EMCS System | [5 empty] | DATE SIGNED |  | INSTALLATIONS ENGINEERS' SIGNATURE
2. STARTING DATE |  | 2025-09-18
3. COMPLETION DATE |  | 2027-03-17 | 9. SUBMITTED BY: (Enter Company Name Here)
4. PURCHASE REQUEST NO. |  | F1T2AZ5097A001 | DATE SIGNED | CONTRACTOR'S NAME (Last, First, Middle Initial) |  | CONTRACTOR'S SIGNATURE |  |  | 11. APPROVED BY:
5. PROJECT NO. |  |  | 2025-09-18 | Collins, Timothy, J. |  |  |  |  | DATE SIGNED |  | CONTRACTING OFFICER'S SIGNATURE
6. ACTUAL STARTING DATE |  |  |  | ADDRESS (Street, City, State, Zip Code)
7. ACTUAL COMPLETION DATE |  |  |  | 2615 Tambridge Circle Pensacola, Fl 32503
Block 12, Schedule Information
LINE NO. | WORK ELEMENTS |  |  |  | % | (D) MONTHLY SCHEDULE (to include percentage of work performed for each Line No.)
(A) | (B) |  |  |  | (C) | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
1 | Submittals/Engineering |  |  |  | 10% |  |  |  | 10%
2 | Niagara N4 Supervisor / JACE Setup |  |  |  | 8% |  |  |  |  | 8%
3 | Material Procurement |  |  |  | 18% |  |  |  | 4% | 5% | 5% | 4%
4 | Network & Installation Materials |  |  |  | 7% |  |  |  | 2% | 3% | 2%
5 | Field Device Installation |  |  |  | 20% | [5 empty] | 2% | 3% | 4% | 4% | 4% | 3%
6 | Controls Programming & Database |  |  |  | 15% | [5 empty] | 2% | 3% | 4% | 3% | 3%
7 | Graphics / UI Development |  |  |  | 6% | [8 empty] | 2% | 2% | 2%
8 | Checkout & PreFunctional Testing |  |  |  | 6% | [10 empty] | 2% | 2% | 2%
9 | PVT / Commissioning |  |  |  | 6% | [12 empty] | 2% | 2% | 2%
10 | As-Builts, O&M Turnover |  |  |  | 4% | [14 empty] | 2% | 1% | 1%
11
12
13
14
COMPLETION OF THE PROJECT |  |  |  |  | 100% | 0% | 0% | 0% | 16% | 16% | 11% | 10% | 8% | 9% | 9% | 7% | 2% | 4% | 2% | 4% | 1% | 1% | 0%
[6 empty] | 0% | 0% | 0% | 16% | 32% | 43% | 53% | 61% | 70% | 79% | 86% | 88% | 92% | 94% | 98% | 99% | 100% | 100%
AF Form 3064, 20030901 PREVIOUS EDITION IS OBSOLETE

## AF3064 Instructions (hidden)
AF Form 3064 Instructions
Block 1 | Contract Number | Enter contract number AF3064 is being accomplish for
Block 2 | Starting Date | Enter anticipated start date
Block 3 | Completion Date | Enter anticipated completion date
Block 4 | Purchase Request No. | Enter Purchase Requisition No. (normally found within CLIN description of contract)
Block 5 | Project No. | Enter Project No. (normally found within CLIN description of contract)
Block 6 | Actual Starting Date | Enter Actual Start Date (provided on Notice to Proceed, when issued)
Block 7 | Actual Completion Date | Enter Completion Date (provided on Notice to Proceed, when issued)
Block 8 | Project Title | Enter Project Title
Block 9 | Submitted By | Enter Company Name next to "SUBMITTED BY:" Enter Contractor POC name under "Contractor's Name" using format provided Enter Contractor Address under "Address" using format provided Date Signed (enter date once AF3065 has been reviewed and finalized Contractor's Signature (Convert AF3065 to PDF and sign once it has been reviewed/finalized)
Block 10 | CES / Vectrus Signature | To be completed by CES / Vectrus personnel after Block 9 has been completed
Block 11 | CO Signature | To be completed by 81 CONS / CO after Block 10 has been completed
Block 12 | Schedule Information | Enter information within the sub-blocks as necessary
Block 12A | Line No. | Numerical numbering used for identification of each work element and completion %
Block 12B | Work Elements | Enter description for each main work element performed under this contract (The descriptions used in this section will also be used on the AF3065)
Block 12C | Percentage of Total Contract | Enter percentage of work that each work element identified in Block 12B represents of the total contract For instance: Line 1 equals 5% of the total contract (normally based on price of work element vs total contract)
Block 12D | Percentage by Month | Enter percentage of work to be accomplished each Month for each work element. For instance: Line 1 is accomplished the first Month then enter 5% in that week's column If Line 2 will take multiple months to accomplish then enter the % to be completed each month in the respective month column
Completion of the Project |  | Percentages in this row calculate automatically based on information entered in Block 12C and Block 12D