1. BACKUP DETAIL SHEET (ATTACH ONLY IF NEEDED)

This is your “show your work” document.
Clean, simple, no fluff.

ATTACHMENT A – COST SUPPORT DETAIL

Project: NAS B832 Fitness Center
Contractor: The Controls Company, LLC

1. Remobilization / Unproductive Trips

| Basis | Value |
| --- | --- |
| Confirmed trips (QuickBooks Time) | 8 |
| Additional field & supervisory trips | 6–7 |
| Total Trips Used | 14–15 |
| Avg crew impact | 1.5 persons |
| Avg inefficiency per trip | 4 hours |
| Fully burdened labor rate | $56/hr |

Calculation:
14–15 trips × 1.5 × 4 hrs × $56/hr = $4,700 – $5,000
Carried Value: $4,900

2. Labor Escalation

| Basis | Value |
| --- | --- |
| Original rate | $39.18/hr |
| Current rate | $42.95/hr |
| Increase | $3.77/hr |
| Estimated total hours | 445 hrs |
| % impacted by delay | 75% |

Calculation:
334 hrs × $3.77 = $1,259
Carried Value: $1,250

3. Productivity / Access Inefficiency

| Basis | Value |
| --- | --- |
| Total estimated hours | 445 hrs |
| Inefficiency factor | 15% |
| Hours impacted | 67 hrs |
| Burdened labor rate | $56/hr |

Calculation:
67 hrs × $56 = $3,752
Carried Value: $3,750

4. Rebadging / Access Processing

| Basis | Value |
| --- | --- |
| Rebadging events | 2 |
| Personnel impacted | 2–3 |
| Avg time per event | 3 hrs |
| Burdened rate | $56/hr |

Calculation:
2 × 2.5 × 3 × $56 = $840
Carried Value: $900

5. Project Management / Coordination

| Basis | Value |
| --- | --- |
| Estimated additional hours | 30–40 hrs |
| Burdened PM rate | $85–$95/hr |

Calculation:
~35 hrs × $90/hr = $3,150
Carried Value: $3,200

6. Material Escalation

| Basis | Value |
| --- | --- |
| Original material value | $8,234 |
| Escalation factor | 12–15% |

Calculation:
$8,234 × 12–15% = $988 – $1,235
Carried Value: $1,100

7. Field Trailer (Extended Duration)

| Basis | Value |
| --- | --- |
| Mobilized | Jan 16, 2026 |
| Duration | ~2.75 months |
| Monthly cost | $500–$650 |

Calculation:
2.75 × $500–$650 = $1,375 – $1,787
Carried Value: $1,600

🧠 IMPORTANT:

This sheet shows:

- You used real data where available

- You used reasonable assumptions where needed

- You were not aggressive

🎯 2. PUSHBACK RESPONSE PLAYBOOK

Here’s exactly how to respond depending on what they say.

🟥 Pushback #1:

“We don’t see that many trips”

Response:

The trip count is based on confirmed QuickBooks Time entries supplemented by known supervisory and management site visits that are not tracked in the time system.

The pricing uses an average inefficiency per mobilization rather than attempting to capture every individual hour, which we felt was a more reasonable and conservative approach.

🟥 Pushback #2:

“Your labor rate seems high”

Response:

The labor rate shown is a fully burdened field labor rate that includes payroll burden, insurance, and field support costs.

It reflects our actual cost of deploying labor to the project, not base wage.

🟥 Pushback #3:

“You already included labor in your contract”

Response:

Correct — the original contract included labor based on a continuous workflow and standard project duration.

The additional labor costs in this request are specifically tied to inefficiencies, remobilizations, and extended duration that were not part of the original assumptions.

🟥 Pushback #4:

“We don’t typically pay for inefficiency”

Response:

Understood — and we’ve made an effort to quantify only inefficiencies directly tied to project conditions such as access restrictions, remobilizations, and out-of-sequence work.

These are measurable impacts resulting from how the work had to be executed, not general productivity assumptions.

🟥 Pushback #5:

“Rebadging is part of working on base”

Response:

Initial badging is anticipated; however, repeated badging cycles due to expiration over an extended project duration were not.

The additional administrative processing and lost field time are directly tied to the extended schedule.

🟥 Pushback #6:

“We can only allow lower profit”

(You’re already ahead here)

Response:

Understood — we’ve already reduced the visible profit and focused this request on actual cost impacts to keep it aligned with project expectations.

🟥 Pushback #7 (Most Likely):

“This number feels high”

Response:

We’ve made a conscious effort to keep this request limited to direct, quantifiable impacts only.

If helpful, we can walk through any specific category in more detail and adjust based on alignment with the project team.