📄 CHANGE ORDER REQUEST

The Controls Company, LLC
Project: NAS B832 Fitness Center
Customer: Siemens
Original Proposal Date: July 20, 2023 
Contract Reference: November 11, 2022

Subject:

Change Order Request – Schedule Delay Impacts & Extended Duration Costs

Summary

The Controls Company is submitting this change order request to recover costs associated with extended project duration, out-of-sequence work, and inefficiencies encountered during execution of the DDC Controls scope.

The original proposal was based on a reasonably continuous workflow, normal working hours, and standard project duration. Since contract execution, the project has extended significantly and has been impacted by access constraints, remobilizations, and evolving site conditions beyond our control.

These impacts have resulted in measurable increases in labor, coordination, and field support costs.

Description of Impacts

1. Extended Project Duration

- Project duration extended significantly beyond original anticipated timeline

- Work performed across multiple phases rather than continuous execution

2. Remobilization & Out-of-Sequence Work

- Multiple return trips required due to incomplete work areas and trade coordination

- Inefficient labor utilization caused by fragmented workflow

3. Base Access & Rebadging Requirements

- Repeated badging cycles due to expiration of credentials

- Administrative processing and access delays impacting field productivity

- Additional coordination required to maintain workforce access

4. Labor Inefficiency / Reduced Productivity

- Trade stacking and restricted work areas

- Partial work completion requiring return visits

- Base access procedures limiting productive work time

5. Project Management & Coordination Impacts

- Extended duration increased coordination, scheduling, and communication requirements

- Project management transition required due to prolonged schedule

- Additional onboarding and re-coordination effort

6. Material & Labor Cost Escalation

- Increased labor rates over extended project duration

- Escalation in material pricing (conduit, wire, fittings)

7. Extended Field Presence (Trailer)

- Field trailer mobilized to site January 16, 2026

- Required to maintain continuous project readiness due to uncertain work availability

💰 Cost Breakdown

| Description | Amount |
| --- | --- |
| Remobilization / Unproductive Trips | $4,900 |
| Labor Escalation | $1,250 |
| Productivity / Access Inefficiency | $3,750 |
| Rebadging / Access Processing | $900 |
| Project Management & Coordination | $3,200 |
| Material Escalation | $1,100 |
| Extended Field Trailer | $1,600 |
| Subtotal (Cost) | $16,700 |
| Overhead (10%) | $1,670 |
| Profit (10%) | $3,130 |
| TOTAL CHANGE ORDER | $21,500 |

Clarifications

- This request reflects only direct impacts associated with project delay, inefficiency, and extended duration

- Costs are based on actual field conditions and reasonable industry-standard assumptions

- This request does not include costs associated with original scope execution

- Pricing is consistent with contract structure and standard markups

Closing

The Controls Company remains committed to successful completion of this project and values our continued partnership with Siemens and the project team.

We appreciate your review and look forward to working collaboratively toward resolution of this request.

Submitted By:
Timothy J. Collins, MBA
President
The Controls Company, LLC